## TestCase
Product Name |  | Othoba E-commerce | TC Start Date | 2024-08-09 | TC Execution Start Date | 2024-10-09 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 2024-09-09 | TC Execution End Date | 2022-11-09 |  |  |  |  | PASS | 31
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 11
Developer Name (TL) |  |  |  |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 42
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Register | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Asterisk sign should be present | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website | Asterisk sign error |  | Failed
5 |  |  |  | Verifying the font size and font style | should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
6 |  |  |  | Cheking backgroung color of register part | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
7 |  |  |  | Cheking backgroung color of sign in part | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
8 |  |  |  | Checking alignment of the fields | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
9 |  |  |  | Cheking backgroung color of register button | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the register background color |  |  | Passed
|  |  |  | Checking 'Newsletter' checkbox is not enabled by default | Should not be enabled by default | Not found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check the register background color | Selected error |  | Failed
44
45
46
47
48 |  | Usability Testing
49
50
51 |  | Functionality Testing | Register | Try to register with valid phone number | Should be register successfully | Found as per expectation | 1689180225 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
52 |  |  |  | Try to register with invalid phone number | Should not register and given error message | Found as per expectation | 168918022 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Try to register with existing phone number | Should not register and given error message | Found as per expectation | 1689180225 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
53 |  |  |  | Verify phone field is correct format | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
54 |  |  |  | Verify email field is correct format | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
55 |  |  |  | Verify phone field with blank splce | Should not register and given error message | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
56 |  |  |  | Verify phone field with white splce | Should not register and given error message | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
57 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provided input | Found as per expectation | tAhsan | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
58 |  |  |  | Entering blank at first position in firstname and lastname field | Should not accept the provided input | Not found as per requirement | Tahsan Hossain | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Blank space error |  | Failed
59 |  |  |  | Entering blank at last position of firstname and lastname field | Should not accept the provided input | Not found as per requirement | Tahsan Sourov | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Last position blank space error |  | Failed
60 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
61 |  |  |  | Inputing firstname and lastname with special characters | Should not accept the provided input | Not found as per expectation | !@#$% %&*$! | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Special character error |  | Failed
|  |  |  | Inputing firstname and lastname with numbers | Should not accept the provided input | Not found as per expectation | 90 88 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Number error |  | Failed
|  |  |  | Inputing firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expectation | 56.88.99 20.40.60 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Decimal error |  | Failed
62 |  |  |  | Inputing firstname and lastname with alphanumeric characters | Should accept the provided input | Found as per expectation | Sagor88 Sumon44 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | Tahsan Sourov | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Entering comma between alphabets for firstname and lastname | Should not accept the provided input | Not found as per expectation | Tah,san Sou,rov | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Comma error |  | Failed
|  |  |  | Entering space between alphabets for firstname and lastname | Should accept the provided input | Found as per expectation | Tah san Sou rov | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Verify date of birth field working properly | Shoulb be as per requirement | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Verify passward and confirm passward field with same passward | should be work properly and match password | Found as per expectation | 123456 123456 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Verify passward and confirm passward field with different passward | Should be given error message | Found as per expectation | 123456 234567 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Passed
|  |  |  | Verify login with valid phone number | Should allow user to login | Found as per expectation | 1689180225 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | verify login with invalid phone number | Should not allow user to login | Found as per expectation | 1689280886 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | Verify login with correct passward | Should allow user to login | Found as per expectation | 123456 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | Verify login with wrong passward | Should not allow user to login | Found as per expectation | 234567 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | Verify login with valid phone number and wrong passward | Should not allow user to login | Found as per expectation | 01689180225 234567 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | Verify login with invalid phone number and correct passward | Should not allow user to login | Found as per expectation | 01689180888 123456 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | Verify login with valid email and valid password | Should allow user to login | Not found as per expectation | nahidhn77@gmail.com 123456 | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner | Error |  | Failed
|  |  |  | Verify Forgot passward field present | Should be present present | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  |  | Verify Forgot passward field working | Should be working Forgot passward field | Found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  | Passed
|  |  | Improvement Scopes | Verify password mask in password section | Should be present | Not found as per expectation | N/A | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner | Error |  | Failed
|  |  |  | Verify password without any letter and special character | Should not accept given password | Not found as per expectation | 123456 | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner |  |  | Failed
Negative test

## Report
Test Case Report
Project Name | Othoba E-commerce
Module Name | Register and Sign In |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 31 | PASS
Written By | [5 empty] | 11 | FAIL
Executed By | [5 empty] | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 31 | 11 | 0 | 0 | 42
Grand Total | 31 | 11 | 0 | 0 | 42
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%) | sprint 001
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (42/42)*100 = 100 | 100 | 60
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/42)*100 = 0 | 60/100*100
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (31/42)*100 =73.80
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (11/42)*100 = 26.19
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/42)*100 = 0 | Version =1 |  | Version 2
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A | 62 /62 |  | 0/62
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Bug Report
Bug Reporting |  |  |  |  | Bug Reporting | Bug Reporting
# SL 56 |  |  |  |  | # SL 12 | # SL 40
Issue: Verify login with valid email and valid password |  |  |  |  | Issue: Verifying mandatory field is marked with a red asterisk | Issue: Inputing firstname and lastname with special characters
| Dev | QA | UAT | live
Reproducing Steps: |  | QA2 |  |  | Reproducing Steps: | Reproducing Steps:
1. Goto the URL https://www.othoba.com/ 2. Click on Sign in button at the right corner |  |  |  |  | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner 3. Check mandatory field is marked with asterik sign or not. | 1. Goto the URL https://www.othoba.com/ 2. Click on Register button at the right corner
Env: https://www.othoba.com/register |  |  |  |  | Env: https://www.othoba.com/register | Env: https://www.othoba.com/register
Module: Sign In |  |  |  |  | Module: Register | Module: Register
Severity: P1 |  |  |  |  | Severity: P2 | Severity: P2
screenshot: Error |  |  |  |  | screenshot: Error | Screenshot: Error
Responsible QA: Tahsan |  |  |  |  | Responsible QA: Tahsan | Responsible QA: Tahsan